## Summary
PIR-LAB Patch Plan Summary
Generated | 2026-06-18 12:07
Management subnet | 192.168.77.0/24
Gateway | PIR-LAB-GW77.1 / 192.168.77.1
Static infrastructure range | 192.168.77.1-192.168.77.99
Suggested DHCP pool | 192.168.77.100-192.168.77.199
Avoided / upstream ranges | 192.168.10.0/23 is already used upstream via 192.168.10.1; do not use 192.168.50.0/24
Metric | Value | Status | Count
Devices | 10 | Planned
VLANs | 6 | In Progress
Planned links | 9 | Confirmed
Core switch | PIR-LAB-CORE77.2 | Needs Check
Default next hop | 192.168.77.1 | Retired

## Patch Plan
Patch Plan
现场用法：先按 Order 接线；接完后把 Status 从 Planned 改为 Confirmed，并填写实际颜色、端口或备注。
Order | Cable ID | Status | From Device | From Port | To Device | To Port | Media | Color | VLAN / Trunk | Purpose | Verification | Notes
1 | CBL-PIR-GW77-1-CORE77-2 | Planned | PIR-LAB-GW77.1 | lan1 | PIR-LAB-CORE77.2 | Gi1/0/48 | Copper | Blue | VLAN 77 access now; phase 2 trunk 77,78,79,80,81,82 | iStoreOS uplink to core | Ping 192.168.77.1 from core; ping 192.168.77.2 from laptop | iStoreOS WAN is upstream under 192.168.10.0/23; LAN to lab is 192.168.77.1
2 | CBL-PIR-CORE77-2-DIST77-3 | Planned | PIR-LAB-CORE77.2 | Gi1/0/49 | PIR-LAB-DIST77.3 | Gi0/49 | Fiber/SFP | Aqua | Trunk allow 77,78,79,80,81,82 | Core to 3560G distribution | CDP neighbor correct; VLAN 77 reachable | Use copper if SFPs are unavailable
3 | CBL-PIR-CORE77-2-DIST77-4 | Planned | PIR-LAB-CORE77.2 | Gi1/0/50 | PIR-LAB-DIST77.4 | Gi0/1 | Fiber/SFP | Aqua | Trunk allow 77,78,79,80,81,82 | Core to 3560 PoE distribution | CDP neighbor correct; VLAN 77 reachable | 3560 uplinks are SFP Gi0/1-Gi0/4
4 | CBL-PIR-CORE77-2-ACC77-5 | Planned | PIR-LAB-CORE77.2 | Gi1/0/51 | PIR-LAB-ACC77.5 | Gi1/0/49 | Fiber/SFP | Aqua | Trunk allow 77,78,79,80,81,82 | Core to 2960-X access 1 | CDP neighbor correct; VLAN 77 reachable | Use first SFP uplink on ACC77.5
5 | CBL-PIR-CORE77-2-ACC77-6 | Planned | PIR-LAB-CORE77.2 | Gi1/0/52 | PIR-LAB-ACC77.6 | Gi1/0/49 | Fiber/SFP | Aqua | Trunk allow 77,78,79,80,81,82 | Core to 2960-X access 2 | CDP neighbor correct; VLAN 77 reachable | Use first SFP uplink on ACC77.6
6 | CBL-PIR-CORE77-2-RTR77-11 | Planned | PIR-LAB-CORE77.2 | Gi1/0/11 | PIR-LAB-RTR77.11 | Gi0/0 | Copper | Yellow | Access VLAN 77 | 1911 management / lab uplink | Ping 192.168.77.11 | Do not enable DHCP/NAT on router
7 | CBL-PIR-CORE77-2-RTR77-12 | Planned | PIR-LAB-CORE77.2 | Gi1/0/12 | PIR-LAB-RTR77.12 | Fa0/0 | Copper | Yellow | Access VLAN 77 | 2811 router management | Ping 192.168.77.12 | 2811 FE port is 100M
8 | CBL-PIR-CORE77-2-VGW77-13 | Planned | PIR-LAB-CORE77.2 | Gi1/0/13 | PIR-LAB-VGW77.13 | Fa0/0 | Copper | Yellow | Access VLAN 77 | 2811 voice gateway management | Ping 192.168.77.13 | Voice gateway role can change later
9 | CBL-PIR-CORE77-2-CUCM77-20 | Planned | PIR-LAB-CORE77.2 | Gi1/0/20 | PIR-LAB-CUCM77.20 | eth0 | Copper | Purple | Access VLAN 77 initially | CUCM server LAN | Ping 192.168.77.20; web login reachable | Later route phones from VLAN 20 to CUCM

## Device Inventory
Device Inventory
TraceEveryLink 里保留带点号的显示名；如果 Cisco IOS hostname 不接受点号，用 Cisco-safe Hostname。
Role | TraceEveryLink Name | Cisco-safe Hostname | Management IP | Vendor | Model | Rack | U Position | Purpose | Notes
Gateway | PIR-LAB-GW77.1 | PIR-LAB-GW77-1 | 192.168.77.1 | iStoreOS | iStoreOS router | External / upstream |  | VLAN 77 gateway and NAT | WAN sits under existing 192.168.10.0/23 office network; LAN is 192.168.77.1 for PIR lab
Core switch | PIR-LAB-CORE77.2 | PIR-LAB-CORE77-2 | 192.168.77.2 | Cisco | WS-C3750G-48TS-S | PIR-LAB-R01 | U42 | Core / trunk center | Confirm exact 3750 SKU from chassis label
Distribution switch | PIR-LAB-DIST77.3 | PIR-LAB-DIST77-3 | 192.168.77.3 | Cisco | WS-C3560G-48TS-S | PIR-LAB-R01 | U41 | Gigabit distribution | 48 x Gi downlinks + SFP uplinks
Distribution switch | PIR-LAB-DIST77.4 | PIR-LAB-DIST77-4 | 192.168.77.4 | Cisco | WS-C3560-48PS-S | PIR-LAB-R01 | U40 | PoE / voice distribution | Good place to test phones and voice VLAN
Access switch | PIR-LAB-ACC77.5 | PIR-LAB-ACC77-5 | 192.168.77.5 | Cisco | WS-C2960X-48FPS-L | PIR-LAB-R01 | U39 | Access switch 1 | Office / phone endpoints
Access switch | PIR-LAB-ACC77.6 | PIR-LAB-ACC77-6 | 192.168.77.6 | Cisco | WS-C2960X-48FPS-L | PIR-LAB-R01 | U38 | Access switch 2 | Spare access / trunk experiments
Router | PIR-LAB-RTR77.11 | PIR-LAB-RTR77-11 | 192.168.77.11 | Cisco | CISCO1911/K9 | PIR-LAB-R01 | U36 | Router lab | Confirm exact 1900-series SKU from chassis label
Router | PIR-LAB-RTR77.12 | PIR-LAB-RTR77-12 | 192.168.77.12 | Cisco | CISCO2811/K9 | PIR-LAB-R01 | U35 | Router lab | 2811 routed-network experiments
Voice gateway | PIR-LAB-VGW77.13 | PIR-LAB-VGW77-13 | 192.168.77.13 | Cisco | CISCO2811/K9 | PIR-LAB-R01 | U34 | Voice gateway candidate | For CUCM, SRST, FXO/FXS, SIP gateway tests
CUCM server | PIR-LAB-CUCM77.20 | PIR-LAB-CUCM77-20 | 192.168.77.20 | Cisco | CUCM 7.4 | PIR-LAB-R01 | U31-U32 | Call manager | Keep on VLAN 77 first; move or route to voice VLAN later

## VLAN IP Plan
VLAN IP Plan
先只启用 VLAN 77 管理网；其他 VLAN 等所有设备可管理后再逐步打开。
VLAN | Name | Subnet | Gateway | Purpose | Phase | Notes
77 | MGMT | 192.168.77.0/24 | 192.168.77.1 | Device management | Phase 1 active | Keep static infra in .1-.99; DHCP clients .100-.199
78 | LAB-CLIENT | 192.168.78.0/24 | 192.168.78.1 | Lab PCs and test clients | Future | Avoids occupied 192.168.10.0/23
79 | VOICE | 192.168.79.0/24 | 192.168.79.1 | IP phones and CUCM/SRST labs | Future | Use as voice VLAN on access ports later
80 | LAB-RTR | 192.168.80.0/24 | 192.168.80.1 | Routed lab segments | Future | Good for routed lab links and experiments
81 | SERVER | 192.168.81.0/24 | 192.168.81.1 | Servers, VMs, and services | Future | Put monitoring, TFTP, syslog, backup boxes here
82 | WIFI-IOT | 192.168.82.0/24 | 192.168.82.1 | Wi-Fi, IoT, and temporary devices | Future | Replaces old 192.168.50.0/24 idea

## Switch Port Plan
Switch Port Plan
核心口先按简单可通方案配置；后续要玩多 VLAN 时再把上联切 trunk。
Device | Port / Range | Mode | Access VLAN | Voice VLAN | Native VLAN | Allowed VLANs | Connected To | Purpose | Notes
PIR-LAB-CORE77.2 | Gi1/0/48 | Access first / trunk later | 77 now |  | 77 if trunk later | 77,78,79,80,81,82 | PIR-LAB-GW77.1 lan1 | Uplink to iStoreOS | Start simple with access VLAN 77; if trunking to iStoreOS later, avoid upstream 192.168.10.0/23
PIR-LAB-CORE77.2 | Gi1/0/49 | Trunk |  |  | 77 | 77,78,79,80,81,82 | PIR-LAB-DIST77.3 Gi0/49 | Distribution uplink | Core to 3560G
PIR-LAB-CORE77.2 | Gi1/0/50 | Trunk |  |  | 77 | 77,78,79,80,81,82 | PIR-LAB-DIST77.4 Gi0/1 | Distribution uplink | Core to 3560 PoE
PIR-LAB-CORE77.2 | Gi1/0/51 | Trunk |  |  | 77 | 77,78,79,80,81,82 | PIR-LAB-ACC77.5 Gi1/0/49 | Access uplink | Core to 2960-X #1
PIR-LAB-CORE77.2 | Gi1/0/52 | Trunk |  |  | 77 | 77,78,79,80,81,82 | PIR-LAB-ACC77.6 Gi1/0/49 | Access uplink | Core to 2960-X #2
PIR-LAB-CORE77.2 | Gi1/0/11 | Access | 77 |  |  |  | PIR-LAB-RTR77.11 Gi0/0 | 1911 management | Router default route to 192.168.77.1
PIR-LAB-CORE77.2 | Gi1/0/12 | Access | 77 |  |  |  | PIR-LAB-RTR77.12 Fa0/0 | 2811 management | 100M endpoint is fine
PIR-LAB-CORE77.2 | Gi1/0/13 | Access | 78 | 79 |  |  | PIR-LAB-VGW77.13 Fa0/0 | Voice gateway management | Can later join voice lab
PIR-LAB-CORE77.2 | Gi1/0/20 | Access | 77 |  |  |  | PIR-LAB-CUCM77.20 eth0 | CUCM management/LAN | Keep stable before phone testing
PIR-LAB-DIST77.3 | Gi0/1-Gi0/24 | Access | 78 |  |  |  | Office/test devices | Office client ports | Use after VLAN 78 is created
PIR-LAB-DIST77.3 | Gi0/25-Gi0/36 | Access | 80 |  |  |  | Router lab devices | Lab routed segment | Use for experiments
PIR-LAB-DIST77.4 | Fa0/1-Fa0/24 | Access + voice | 78 | 79 |  |  | PC + phone pairs | Voice lab access | Requires voice VLAN 79 config
PIR-LAB-ACC77.5 | Gi1/0/1-Gi1/0/24 | Access | 78 |  |  |  | Office/test endpoints | Client access | Phase 2
PIR-LAB-ACC77.5 | Gi1/0/25-Gi1/0/36 | Access + voice | 78 | 79 |  |  | IP phone + PC | Voice access | Phase 2
PIR-LAB-ACC77.5 | Gi1/0/37-Gi1/0/48 | Access | 82 |  |  |  | Temporary devices | Wi-Fi/IoT/temp | Phase 2
PIR-LAB-ACC77.6 | Gi1/0/1-Gi1/0/24 | Access | 78 |  |  |  | Office/test endpoints | Client access | Phase 2
PIR-LAB-ACC77.6 | Gi1/0/25-Gi1/0/36 | Access + voice | 78 | 79 |  |  | IP phone + PC | Voice access | Phase 2
PIR-LAB-ACC77.6 | Gi1/0/37-Gi1/0/48 | Access | 80 or 82 |  |  |  | Lab/temp devices | Flexible spare block | Label before use

## Config Checklist
Config Checklist
把 Status 当现场配置进度用；强密码、真实 SNMP、NTP、备份策略后续再补。
Device | Area | Task | Command / Target | Status | Notes
PIR-LAB-CORE77.2 | Base identity | Set hostname | hostname PIR-LAB-CORE77-2 | Planned | Use hyphen form if IOS rejects dot in hostname
PIR-LAB-CORE77.2 | Management | Configure management IP | VLAN 77 / management interface -> 192.168.77.2/24; gateway 192.168.77.1 | Planned | Use interface VLAN 77 for switches; routed interface for routers
PIR-LAB-CORE77.2 | Security | Create local admin and enable remote access | username admin privilege 15 secret <strong-password>; transport input ssh telnet | Planned | Prefer SSH once crypto keys are set
PIR-LAB-CORE77.2 | Save | Save config | write memory | Planned | Record final running-config backup later
PIR-LAB-DIST77.3 | Base identity | Set hostname | hostname PIR-LAB-DIST77-3 | Planned | Use hyphen form if IOS rejects dot in hostname
PIR-LAB-DIST77.3 | Management | Configure management IP | VLAN 77 / management interface -> 192.168.77.3/24; gateway 192.168.77.1 | Planned | Use interface VLAN 77 for switches; routed interface for routers
PIR-LAB-DIST77.3 | Security | Create local admin and enable remote access | username admin privilege 15 secret <strong-password>; transport input ssh telnet | Planned | Prefer SSH once crypto keys are set
PIR-LAB-DIST77.3 | Save | Save config | write memory | Planned | Record final running-config backup later
PIR-LAB-DIST77.4 | Base identity | Set hostname | hostname PIR-LAB-DIST77-4 | Planned | Use hyphen form if IOS rejects dot in hostname
PIR-LAB-DIST77.4 | Management | Configure management IP | VLAN 77 / management interface -> 192.168.77.4/24; gateway 192.168.77.1 | Planned | Use interface VLAN 77 for switches; routed interface for routers
PIR-LAB-DIST77.4 | Security | Create local admin and enable remote access | username admin privilege 15 secret <strong-password>; transport input ssh telnet | Planned | Prefer SSH once crypto keys are set
PIR-LAB-DIST77.4 | Save | Save config | write memory | Planned | Record final running-config backup later
PIR-LAB-ACC77.5 | Base identity | Set hostname | hostname PIR-LAB-ACC77-5 | Planned | Use hyphen form if IOS rejects dot in hostname
PIR-LAB-ACC77.5 | Management | Configure management IP | VLAN 77 / management interface -> 192.168.77.5/24; gateway 192.168.77.1 | Planned | Use interface VLAN 77 for switches; routed interface for routers
PIR-LAB-ACC77.5 | Security | Create local admin and enable remote access | username admin privilege 15 secret <strong-password>; transport input ssh telnet | Planned | Prefer SSH once crypto keys are set
PIR-LAB-ACC77.5 | Save | Save config | write memory | Planned | Record final running-config backup later
PIR-LAB-ACC77.6 | Base identity | Set hostname | hostname PIR-LAB-ACC77-6 | Planned | Use hyphen form if IOS rejects dot in hostname
PIR-LAB-ACC77.6 | Management | Configure management IP | VLAN 77 / management interface -> 192.168.77.6/24; gateway 192.168.77.1 | Planned | Use interface VLAN 77 for switches; routed interface for routers
PIR-LAB-ACC77.6 | Security | Create local admin and enable remote access | username admin privilege 15 secret <strong-password>; transport input ssh telnet | Planned | Prefer SSH once crypto keys are set
PIR-LAB-ACC77.6 | Save | Save config | write memory | Planned | Record final running-config backup later
PIR-LAB-RTR77.11 | Base identity | Set hostname | hostname PIR-LAB-RTR77-11 | Planned | Use hyphen form if IOS rejects dot in hostname
PIR-LAB-RTR77.11 | Management | Configure management IP | VLAN 77 / management interface -> 192.168.77.11/24; gateway 192.168.77.1 | Planned | Use interface VLAN 77 for switches; routed interface for routers
PIR-LAB-RTR77.11 | Security | Create local admin and enable remote access | username admin privilege 15 secret <strong-password>; transport input ssh telnet | Planned | Prefer SSH once crypto keys are set
PIR-LAB-RTR77.11 | Save | Save config | write memory | Planned | Record final running-config backup later
PIR-LAB-RTR77.12 | Base identity | Set hostname | hostname PIR-LAB-RTR77-12 | Planned | Use hyphen form if IOS rejects dot in hostname
PIR-LAB-RTR77.12 | Management | Configure management IP | VLAN 77 / management interface -> 192.168.77.12/24; gateway 192.168.77.1 | Planned | Use interface VLAN 77 for switches; routed interface for routers
PIR-LAB-RTR77.12 | Security | Create local admin and enable remote access | username admin privilege 15 secret <strong-password>; transport input ssh telnet | Planned | Prefer SSH once crypto keys are set
PIR-LAB-RTR77.12 | Save | Save config | write memory | Planned | Record final running-config backup later
PIR-LAB-VGW77.13 | Base identity | Set hostname | hostname PIR-LAB-VGW77-13 | Planned | Use hyphen form if IOS rejects dot in hostname
PIR-LAB-VGW77.13 | Management | Configure management IP | VLAN 77 / management interface -> 192.168.77.13/24; gateway 192.168.77.1 | Planned | Use interface VLAN 77 for switches; routed interface for routers
PIR-LAB-VGW77.13 | Security | Create local admin and enable remote access | username admin privilege 15 secret <strong-password>; transport input ssh telnet | Planned | Prefer SSH once crypto keys are set
PIR-LAB-VGW77.13 | Save | Save config | write memory | Planned | Record final running-config backup later
PIR-LAB-GW77.1 | DHCP | Restrict DHCP scope | Serve 192.168.77.100-192.168.77.199 only | Planned | Keep .1-.99 static for infrastructure
PIR-LAB-CUCM77.20 | Server IP | Set static CUCM address | 192.168.77.20/24 gw 192.168.77.1 dns 192.168.77.1 | Planned | Set NTP before voice testing

## TraceEveryLink Import
TraceEveryLink Import
这张可用于和系统里的 planned cables 对照，现场确认后同步改为 confirmed。
Cable ID | Status | From Device | From Port | To Device | To Port | VLAN / Trunk | Purpose
CBL-PIR-GW77-1-CORE77-2 | Planned | PIR-LAB-GW77.1 | lan1 | PIR-LAB-CORE77.2 | Gi1/0/48 | VLAN 77 access now; phase 2 trunk 77,78,79,80,81,82 | iStoreOS uplink to core
CBL-PIR-CORE77-2-DIST77-3 | Planned | PIR-LAB-CORE77.2 | Gi1/0/49 | PIR-LAB-DIST77.3 | Gi0/49 | Trunk allow 77,78,79,80,81,82 | Core to 3560G distribution
CBL-PIR-CORE77-2-DIST77-4 | Planned | PIR-LAB-CORE77.2 | Gi1/0/50 | PIR-LAB-DIST77.4 | Gi0/1 | Trunk allow 77,78,79,80,81,82 | Core to 3560 PoE distribution
CBL-PIR-CORE77-2-ACC77-5 | Planned | PIR-LAB-CORE77.2 | Gi1/0/51 | PIR-LAB-ACC77.5 | Gi1/0/49 | Trunk allow 77,78,79,80,81,82 | Core to 2960-X access 1
CBL-PIR-CORE77-2-ACC77-6 | Planned | PIR-LAB-CORE77.2 | Gi1/0/52 | PIR-LAB-ACC77.6 | Gi1/0/49 | Trunk allow 77,78,79,80,81,82 | Core to 2960-X access 2
CBL-PIR-CORE77-2-RTR77-11 | Planned | PIR-LAB-CORE77.2 | Gi1/0/11 | PIR-LAB-RTR77.11 | Gi0/0 | Access VLAN 77 | 1911 management / lab uplink
CBL-PIR-CORE77-2-RTR77-12 | Planned | PIR-LAB-CORE77.2 | Gi1/0/12 | PIR-LAB-RTR77.12 | Fa0/0 | Access VLAN 77 | 2811 router management
CBL-PIR-CORE77-2-VGW77-13 | Planned | PIR-LAB-CORE77.2 | Gi1/0/13 | PIR-LAB-VGW77.13 | Fa0/0 | Access VLAN 77 | 2811 voice gateway management
CBL-PIR-CORE77-2-CUCM77-20 | Planned | PIR-LAB-CORE77.2 | Gi1/0/20 | PIR-LAB-CUCM77.20 | eth0 | Access VLAN 77 initially | CUCM server LAN

## Labels
Labels
可复制 Label Text 到标签机模板；线缆标签建议两端都贴。
Label Type | Item ID | Label Text | Rack | U Position | Print / Color Notes
Device | PIR-LAB-GW77.1 | PIR-LAB-GW77.1 192.168.77.1 Gateway | External / upstream |  | Print device label
Device | PIR-LAB-CORE77.2 | PIR-LAB-CORE77.2 192.168.77.2 Core switch | PIR-LAB-R01 | U42 | Print device label
Device | PIR-LAB-DIST77.3 | PIR-LAB-DIST77.3 192.168.77.3 Distribution switch | PIR-LAB-R01 | U41 | Print device label
Device | PIR-LAB-DIST77.4 | PIR-LAB-DIST77.4 192.168.77.4 Distribution switch | PIR-LAB-R01 | U40 | Print device label
Device | PIR-LAB-ACC77.5 | PIR-LAB-ACC77.5 192.168.77.5 Access switch | PIR-LAB-R01 | U39 | Print device label
Device | PIR-LAB-ACC77.6 | PIR-LAB-ACC77.6 192.168.77.6 Access switch | PIR-LAB-R01 | U38 | Print device label
Device | PIR-LAB-RTR77.11 | PIR-LAB-RTR77.11 192.168.77.11 Router | PIR-LAB-R01 | U36 | Print device label
Device | PIR-LAB-RTR77.12 | PIR-LAB-RTR77.12 192.168.77.12 Router | PIR-LAB-R01 | U35 | Print device label
Device | PIR-LAB-VGW77.13 | PIR-LAB-VGW77.13 192.168.77.13 Voice gateway | PIR-LAB-R01 | U34 | Print device label
Device | PIR-LAB-CUCM77.20 | PIR-LAB-CUCM77.20 192.168.77.20 CUCM server | PIR-LAB-R01 | U31-U32 | Print device label
Cable | CBL-PIR-GW77-1-CORE77-2 | CBL-PIR-GW77-1-CORE77-2 PIR-LAB-GW77.1 lan1 TO PIR-LAB-CORE77.2 Gi1/0/48 | PIR-LAB-R01 |  | Blue
Cable | CBL-PIR-CORE77-2-DIST77-3 | CBL-PIR-CORE77-2-DIST77-3 PIR-LAB-CORE77.2 Gi1/0/49 TO PIR-LAB-DIST77.3 Gi0/49 | PIR-LAB-R01 |  | Aqua
Cable | CBL-PIR-CORE77-2-DIST77-4 | CBL-PIR-CORE77-2-DIST77-4 PIR-LAB-CORE77.2 Gi1/0/50 TO PIR-LAB-DIST77.4 Gi0/1 | PIR-LAB-R01 |  | Aqua
Cable | CBL-PIR-CORE77-2-ACC77-5 | CBL-PIR-CORE77-2-ACC77-5 PIR-LAB-CORE77.2 Gi1/0/51 TO PIR-LAB-ACC77.5 Gi1/0/49 | PIR-LAB-R01 |  | Aqua
Cable | CBL-PIR-CORE77-2-ACC77-6 | CBL-PIR-CORE77-2-ACC77-6 PIR-LAB-CORE77.2 Gi1/0/52 TO PIR-LAB-ACC77.6 Gi1/0/49 | PIR-LAB-R01 |  | Aqua
Cable | CBL-PIR-CORE77-2-RTR77-11 | CBL-PIR-CORE77-2-RTR77-11 PIR-LAB-CORE77.2 Gi1/0/11 TO PIR-LAB-RTR77.11 Gi0/0 | PIR-LAB-R01 |  | Yellow
Cable | CBL-PIR-CORE77-2-RTR77-12 | CBL-PIR-CORE77-2-RTR77-12 PIR-LAB-CORE77.2 Gi1/0/12 TO PIR-LAB-RTR77.12 Fa0/0 | PIR-LAB-R01 |  | Yellow
Cable | CBL-PIR-CORE77-2-VGW77-13 | CBL-PIR-CORE77-2-VGW77-13 PIR-LAB-CORE77.2 Gi1/0/13 TO PIR-LAB-VGW77.13 Fa0/0 | PIR-LAB-R01 |  | Yellow
Cable | CBL-PIR-CORE77-2-CUCM77-20 | CBL-PIR-CORE77-2-CUCM77-20 PIR-LAB-CORE77.2 Gi1/0/20 TO PIR-LAB-CUCM77.20 eth0 | PIR-LAB-R01 |  | Purple